## Sprint 1
Story No | Task No | Task Description | Status | Owner | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent - Day 6 | Hours Spent - Day 7 | Total Spent Hours
Story1 | Task1 | Login to the system with provided private account or with faculty's guest account. | Closed | Son | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 4
Story2 | Task2 | Admin views all courses. | Closed | Loi | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 4
Story3 | Task3 | Admin creates new course. | Closed | Thanh | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
Story4 | Task4 | Admin edits course. | Closed | Tung | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 4
Story5 | Task5 | Admin filters course. | Closed | Anh | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 5
Story6 | Task6 | Admin assigns course to faculty. | Closed | Loi | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 4
Story7 | Task7 | Admin assigns CL, CM to manage course. | Closed | Thanh | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4
|  |  |  | Actual Remaining Hours | 29 | 21 | 14 | 6 | 3 | 2 | 1 | 0
|  |  |  | Estimated Remaining Hours | 29 | 24.85714286 | 20.71428571 | 16.57142857 | 12.42857143 | 8.285714286 | 4.142857143 | 0

## Sprint 2
Story No | Task No | Task Description | Status | Owner | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent - Day 6 | Hours Spent - Day 7 | Total Spent Hours
Story8 | Task1 | Admin views all faculties. | Closed | Son | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
Story9 | Task2 | Admin creates new faculty. | Closed | Loi | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 4
Story10 | Task3 | Admin edits faculty. | Closed | Thanh | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
Story11 | Task4 | Admin assigns PVC, DLT to manage faculty. | Closed | Tung | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 4
Story12 | Task5 | Admin views all staffs. | Closed | Anh | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 5
Story13 | Task6 | Admin creates new staff. | Closed | Loi | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
Story14 | Task7 | Admin edits staff. | Closed | Thanh | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4
|  |  |  | Actual Remaining Hours | 29 | 24 | 20 | 12 | 9 | 7 | 3 | 0
|  |  |  | Estimated Remaining Hours | 29 | 24.85714286 | 20.71428571 | 16.57142857 | 12.42857143 | 8.285714286 | 4.142857143 | 0

## Sprint 3
Story No | Task No | Task Description | Status | Owner | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent - Day 6 | Hours Spent - Day 7 | Total Spent Hours
Story15 | Task1 | Admin filters staffs. | Closed | Son | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
Story16 | Task2 | CL views assigned courses. | Closed | Loi | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 4
Story17 | Task3 | CL creates reports. | Closed | Thanh | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
Story18 | Task4 | CL edits reports. | Closed | Tung | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 4
Story19 | Task5 | CL read comments in report. | Closed | Anh | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4
Story20 | Task6 | CM views assigned courses. | Closed | Loi | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
Story21 | Task7 | CM views reports that were sent by CL. | Closed | Thanh | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4
Story22 | Task 8 | CM approves report. | Closed | Son | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
Story23 | Task 9 | CM read comments in report. | Closed | Tung | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
|  |  |  | Actual Remaining Hours | 36 | 31 | 27 | 19 | 16 | 14 | 6 | 0
|  |  |  | Estimated Remaining Hours | 36 | 30.85714286 | 25.71428571 | 20.57142857 | 15.42857143 | 10.28571429 | 5.142857143 | 0

## Sprint 4
Story No | Task No | Task Description | Status | Owner | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent - Day 6 | Hours Spent - Day 7 | Total Spent Hours
Story24 | Task1 | PVC views assigned faculties. | Closed | Son | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
Story25 | Task2 | PVC view reports that were approved by CM. | Closed | Loi | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 4
Story26 | Task3 | PVC reads comments in report. | Closed | Thanh | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
Story27 | Task4 | Director views assigned faculties. | Closed | Tung | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 4
Story28 | Task5 | Director views reports that were approved by CM. | Closed | Anh | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4
Story29 | Task6 | Director comments in report. | Closed | Loi | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
Story30 | Task7 | Director will be reminded to comment before deadline. | Closed | Thanh | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4
Story31 | Task 8 | Guest views all approved reports. | Closed | Son | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
Story32 | Task 9 | Guest views all exceptional reports. | Closed | Tung | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
Story33 | Task10 | Guest views all statistical reports. | Closed | Thanh | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
|  |  |  | Actual Remaining Hours | 40 | 35 | 31 | 23 | 20 | 18 | 8 | 0
|  |  |  | Estimated Remaining Hours | 40 | 34.28571429 | 28.57142857 | 22.85714286 | 17.14285714 | 11.42857143 | 5.714285714 | 0